## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US -01 | Setup project structure and Spark server | MUST HAVE | NA | Riya kumari | 3- Completed
Sprint 1 | Sprint1 | US 02 | Introduction to Java Basics like Exceptions,Collections,OOPS concpet,jdbc basic | MUST HAVE | NA | Riya kumari | 3- Completed
Sprint 1 | Sprint 1 | US -03 | Implement Account class & repository with balance handling | MUST HAVE | US-01 | Riya kumari | 3- Completed
Sprint 1 | Sprint 1 | US -04 | Implement account creation API | MUST HAVE | US -02 | Riya kumari | 3- Completed
Sprint 2 | Sprint 2 | US -05 | Implement deposit functionality | MUST HAVE | US -03 | Riya kumari | 3- Completed
Sprint 2 | Sprint 2 | US -06 | Implement withdrawal functionality with exception handling | MUST HAVE | US -03 | Riya kumari | 3- Completed
Sprint 2 | Sprint 2 | US -07 | Implement transfer functionality between accounts | MUST HAVE | US-04, US-05 | Riya kumari | 3- Completed
Sprint 2 | Sprint 2 | US -08 | Add transaction validation and history logging | MUST HAVE | US-04, US-05 | Riya kumari | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Implement low balance alert service | SHOULD HAVE | US -02 | Riya kumari | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Implement email notification for low balance | SHOULD HAVE | US-08 | Riya kumari | 3- Completed
Sprint4 | Sprint4 | US-11 | Develop simple frontend UI for account and transactions | COULD HAVE | NA | Riya kumari | 3- Completed
Sprint4 | Sprint4 | US-12 | Integrate frontend with backend APIs | SHOULD HAVE | US-10,US-03-US10 | Riya kumari | 2- In Progress
Sprint4 | Sprint4 | US-13 | Perform end-to-end testing of complete workflow | SHOULD HAVE | US-11 | Riya kumari | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 48 | 7 | 7 | 4 | 4 | 7 | 7 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US 01 | 1 | Project setup & GitHub repository initialization | 2025-12-01 | 2025-12-01 | Riya Kumari | Others | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 2 | Java revision (OOP, Collections, Exceptions) | 2025-12-01 | 2025-12-02 | Riya Kumari | Others | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 3 | Spark Java server setup and configuration | 2025-12-02 | Others | Riya | Others | 3- Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 4 | Design Account model (fields & structure) | 2025-12-03 | 2025-12-04 | Riya Kumari | Others | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 5 | Implement Account class in Java | 2025-12-04 | 2025-12-05 | Riya Kumari | Coding | 3- Completed | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 6 | Create AccountRepository using collections | 2025-12-05 | 2025-12-06 | Riya kumari | Coding | 3- Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 7 | Implement Create Account API endpoint | 2025-12-06 | 2025-12-06 | Riya kumari | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 8 | Validate account creation input & errors | 2025-12-08 | 2025-12-09 | Riya kumari | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 9 | Test Account APIs using Postman | 2025-12-09 | 2025-12-10 | Riya kumari | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US 01 | 10 | Sprint 1 review & documentation update | 2025-12-11 | 2025-12-12 | Riya kumari | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint1 | Day2 | Lack of clarity on overall Banking Simulator project requirements and expected features | Discussed requirements with mentor and reviewed reference banking use cases
Sprint 1 | Day4 | Confusion in setting up project structure and Spark server configuration | Reorganized package structure and verified Spark server setup with mentor guidance
Sprint2 | Day6 | Difficulty in designing Account model and repository classes | Studied sample repository patterns and refined Account class design
Sprint 2 | Day7 | Errors while implementing deposit and withdrawal logic | Debugged logic step-by-step and added proper validations and exception handling
Sprint2 | Day9 | Confusion in handling account transfer dependency between multiple accounts | Implemented transfer logic using account lookup and balance checks
Sprint3 | Day12 | Issues while implementing low balance alert service | Reviewed alert workflow and tested threshold logic with sample accounts
Sprint4 | Day16 | Difficulty integrating frontend with backend APIs | Tested APIs using Postman and corrected request/response mapping
Sprint4 | Day18 | Minor issues during end-to-end testing of transactions | Performed repeated test cases and fixed edge-case bugs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-01 | 2025-12-12 | Riya kumari | Reviewing banking requirements and API design before coding | Assuming requirements without validation | Participating in mentor discussions | Clarified BankingSimulator requirements and finalized Account module design
2 | Sprint 2 | 2025-12-15 | 2025-12-19 | Riya kumari | Writing validations before transaction logic | Skipping edge-case testing | Testing deposit and withdrawal APIs frequently | Reduced transaction-related bugs by adding validations
3 | Sprint 3 | 2025-12-22 | 2026-01-02 | Riya kumari | Monitoring balance thresholds during testing | Hardcoding alert values | Reviewing alert logic with mentor | Successfully implemented low-balance alert service
4 | Sprint 4 | 2026-01-05 | 2026-01-16 | Riya kumari | Testing frontend and backend together | Delaying integration testing | Using Postman before frontend integration | Completed frontend-backend integration smoothly
5 | Sprint 4 | 2026-01-19 | 2026-01-23 | Riya kumari | Performing end-to-end test scenarios | Ignoring minor UI issues | Re-testing complete user flow | Identified and fixed integration and UI issues